## Instructions
In order to successfully plan and manage a Project, this tool aligns all partcipants at launch and during the entire project
This Plan is updated weekly, and reviewed with your manager/project manager for what is on track, upcoming, and delayed
File Instructions:
1. "Save" CLIENTCO Project Plan PROJECT NAME in the Planning folder of your client's new Project Folder (not the Project Master)
2. Complete Top Rows with Client details and project name, along with Hyperlinking critical documents to project plan
3. Add/Adjust Phases and Tasks to reflect your project and complete rest of Project Plan
4. As project continues adjust "Actual"
5. Send and use to teammates to keep everyone on track
6. You can create reports for individuals by filtering resource column
7. You can create reports of tasks that are In Progress or Outstanding by filtering Status column
8. To your CLIENTCO Project X Task (in Outlook) add hyperlink to this document for easy access

## Project Plan
Client |  | PROJECT GOAL(S) |  |  |  | DELIVERABLES |  |  | KEY HYPERLINKS to:
Project Title | Blur Project | Compose Project Goal(s) HERE |  |  |  | 1 |  |  | Parameters Doc
Project Start Date | 2024-12-07 |  |  |  |  | 2 |  |  | Phase Completion
Target Delivery Date | [5 empty] | 3 |  |  | Lessons Learned
Project Target Hours | [5 empty] | 4
Project Budget Hours | [5 empty] | 5
Either fill Hours OR Business Days for each entry below
PHASE | Milestone | TASK | Estimated Work Hours | Hour/Day Ratio | ACTUAL Hours | Estimated Business Days | PLANNED START DATE | PLANNED END DATE | RESOURCES | ACTUAL START DATE | ACTUAL END DATE | STATUS | Document Links | Notes/Pre-Requisites
PLANNING | Define App Features & User Flow | Finalize core app features: Care Web, mood tracking, reach out feature, chat | 1 | 0.125 | 5 |  | 2024-12-10 | 2024-12-10 |  | 2024-12-10 | 2024-12-11 | COMPLETE
| Backend Setup & Firebase Integration | Set up Firebase Authentication, Twilio API for messaging, Agora/Jitsi SDK for calls | 1 | 0.125 | 1 |  | 2023-09-30 | 2023-09-30 |  | 2024-01-03 |  | IN PROGRESS
| Wireframing & UI Design | Sketch wireframes and create UI designs for key screens (Onboarding, Profile, Dashboard) | 3 | 0.375 | 1.5 |  | 2023-09-30 | 2023-09-30 |  | 2023-09-30 |  | IN PROGRESS |  |  | Tools
| Basic App Setup & Structure | Set up basic app structure and implement navigation in Flutter | 1 | 0.125 | 0.5 |  | 2023-09-30 | 2023-09-30 |  | 2023-09-30 |  | IN PROGRESS |  |  | Scheduling | Canlendly
ANALYSIS |  | Watch Youtube for current SaaS Models | 2 | 0.25 | 2 |  | 2023-09-30 | 2023-09-30 |  |  |  | COMPLETE |  |  | Development | Webflow, WordPress, Elementor, Canva, Figma
|  | Create SaaS Model | 1 | 0.125 |  |  | 2023-09-30 | 2023-09-30 |  |  |  | NOT STARTED |  |  | Domain | Hostinger
|  | Calculate after first year cost | 1 | 0.125 |  |  | 2023-09-30 | 2023-09-30 |  |  |  | COMPLETE |  | Including domain & host $150/monthly
|  | Analyze editor cost | 1 | 0.125 |  |  | 2023-09-30 | 2023-09-30 | Workspace | 2023-10-16 |  | IN PROGRESS | https://webflow.com/dashboard/workspace/my-workspace-3de14f/plans?ref=plans_tab | Webflow $30/monthly
|  | Analyze second editor cost | 1 | 0.125 | 1 |  | 2023-10-16 | 2023-10-16 | Wordpress | 2023-10-16 |  | IN PROGRESS | https://wordpress.com/pricing/ | Wordpress $42/monthly
|  | Analyze domain & host cost | 1 | 0.125 | 1 |  | 2023-09-30 | 2023-09-30 | Hostinger | 2023-10-16 |  | IN PROGRESS | https://cart.hostinger.com/pay/1f15f5a9-98bb-406a-9bdb-d3a3bf166988 | Hostinger $24/monthly
|  | Competitor Research | 2 | 0.25 |  |  | 2023-09-30 | 2023-09-30 |  |  |  | NOT STARTED
|  | Review current social media | 2 | 0.25 |  |  | 2023-09-30 | 2023-09-30 |  |  |  | NOT STARTED
|  |  |  | 0 |  |  |  | 0 |  |  |  | NOT STARTED
|  |  |  | 0 |  |  |  | 0 |  |  |  | NOT STARTED
|  |  |  | 0 |  |  |  | 0 |  |  |  | NOT STARTED
|  |  |  | 0 |  |  |  | 0 |  |  |  | NOT STARTED
DESIGN | User Onboarding & Care Web Setup | Implement user registration, onboarding, and Care Web setup |  | 0 |  |  |  | 0 |  |  |  | NOT STARTED
| Mood Tracking & Messaging Feature | Create mood tracking UI and 'Reach Out' feature |  | 0 |  |  |  | 0
| Chat & Communication Interface | Design and implement real-time messaging and video calls |  | 0 |  |  |  | 0
| Unit Testing & Debugging | Test individual features (e.g., sign-up, mood tracking, messaging) |  | 0 |  |  |  | 0
| User Acceptance Testing (UAT) | Conduct UAT with users, gather feedback |  | 0 |  |  |  | 0 |  |  |  | NOT STARTED
| Optimization & Performance Tuning | Optimize app performance (API calls, Firebase queries, smooth transitions) |  | 0 |  |  |  | 0 |  |  |  | NOT STARTED
DEPLOY |  | MIDPOINT CHECK-IN FOR HOURS (alloted vs actual) |  | 0 |  |  |  | 0 |  |  |  | NOT STARTED
|  | Upload Survey in TP |  | 0 |  |  |  | 0 |  |  |  | NOT STARTED
|  | Test Survey |  | 0 |  |  |  | 0 |  |  |  | NOT STARTED
|  | Deploy Survey to Target |  | 0 |  |  |  | 0 |  |  |  | NOT STARTED
|  | Send Survey Participation Statistics to Client |  | 0 |  |  |  | 0 |  |  |  | NOT STARTED
EVALUATE |  | Analyze data |  | 0 |  |  |  | 0 |  |  |  | NOT STARTED
|  | Segment Demographic |  | 0 |  |  |  | 0 |  |  |  | NOT STARTED
|  | Advanced Analysis |  | 0 |  |  |  | 0 |  |  |  | NOT STARTED
DELIVER |  | Create Powerpoint |  | 0 |  |  |  | 0 |  |  |  | NOT STARTED
|  | Deliver to Client |  | 0 |  |  |  | 0 |  |  |  | NOT STARTED
|  | Send Client Feedback Email + Link to Client Evaluation Form |  | 0 |  |  |  | 0 |  |  |  | NOT STARTED
|  | Lessons Learned Meeting (bring client feedback) |  | 0 |  |  |  | 0 |  |  |  | NOT STARTED
TOTAL HOURS |  |  | 17 |  | 12 | 0
PROJECT HOURS TARGET |  |  | 0
Formulas:
PLANNED END DATE = IF(Table1[[#This Row],[Estimated Work Hours]]=0,WORKDAY(Table1[[#This Row],[PLANNED START DATE]],Table1[[#This Row],[Estimated Business Days]]),WORKDAY(Table1[[#This Row],[PLANNED START DATE]],Table1[[#This Row],[Hour/Day Ratio]]))

## Field Values
STATUS
COMPLETE
NOT STARTED
IN PROGRESS